## Content
Verdant Hollow - Level & Content Tracker
Owner: Carlos Foster ¦ Build 0.8.3-demo ¦ Updated 2026-02-22 ¦ Target: Early Access November 2026
No | Title | Area | Type | Owner | Status | Launch blocking | Est hrs left | Target date | Notes
1 | Verdant Edge | Act 1 hub | Level | Carlos | delivered | no | 0 | 2025-09-10 | Tutorial cadence locked
2 | First Light Path | Act 1 | Level | Carlos | delivered | no | 0 | 2025-09-24 | Dash introduction
3 | Whispering Canopy | Act 1 | Level | Carlos | delivered | no | 0 | 2025-10-08 | Canopy verticality
4 | Brambleheart | Act 1 miniboss | Boss | Carlos | delivered | no | 0 | 2025-10-22 | Teaches the parry window
5 | Old Stone Shrine | Act 1 | Level | Carlos | delivered | no | 0 | 2025-11-05 | Optional Emberseed pocket
6 | The Glade Below | Act 1 | Level | Carlos | delivered | no | 0 | 2025-11-19 | Act 1 close
7 | Emberseed | Item theme | System | Carlos | delivered | no | 0 | 2025-12-03 | Collectible arc
8 | Sunken Marsh | Act 2 hub | Level | Carlos | delivered | no | 0 | 2025-12-17 | Vertical descent design
9 | Mire and Mist | Act 2 | Level | Carlos | delivered | no | 0 | 2025-12-31 | Water slow shader
10 | Drowned Bell | Act 2 | Level | Carlos | delivered | no | 0 | 2026-01-14 | Narrative beat scene
11 | The Hollow King | Act 2 boss | Boss | Carlos | delivered | no | 0 | 2026-01-28 | Major boss, three phases
12 | Reliquary | Act 2 | Level | Carlos | delivered | no | 0 | 2026-02-04 | Optional lore room
13 | Rain on the Reeds | Act 2 | Level | Carlos | delivered | no | 0 | 2026-02-11 | Audio bus fix pending
14 | Quiet Water | Act 2 rest | Level | Carlos | delivered | no | 0 | 2026-02-18 | Save room, hub link
15 | Ascent | Act 3 | Level | Carlos | scheduled | yes | 40 | 2026-10-10 | Act 3 opens, needs art and audio
16 | Starless Climb | Act 3 | Level | Carlos | scheduled | yes | 44 | 2026-10-10 | Cosmic zone palette
17 | The Cosmic Shelf | Act 3 | Level | Carlos | scheduled | yes | 38 | 2026-10-10 | Set-piece traversal
18 | Far Light | Act 3 | Level | Carlos | scheduled | yes | 30 | 2026-10-10 | Pre-finale ramp
19 | Hollow Crown | Finale boss | Boss | Carlos | pending | yes | 60 | 2026-11-06 | Finale boss, not started
20 | Aftermath | Ending | Level | Carlos | pending | yes | 24 | 2026-11-06 | Ending sequence
21 | Main Theme (full) | Title | Audio | Alex | pending | no | 0 | 2026-11-20 | Soundtrack track 21 of 22
22 | Credits | Credits | System | Carlos | pending | no | 8 | 2026-11-20 | Credits crawl
SUMMARY
Delivered | 14 |  | Scheduled (Act 3) | 4 |  | Pending | 4 |  | Launch-blocking | 8
Est hrs to Early Access | 244 |  | Content items total | 22