## Beta
Verdant Hollow - Beta Feedback Log
Tuesday playtests over Discord ¦ Five testers ¦ Build 0.8.3-demo
Date | Tester | Area | Issue | Severity | Repro % | Assigned | Status
2026-01-13 | pixelwren | Act 2 marsh | Jump arc feels floaty over water | medium | 80 | Carlos | addressed
2026-01-13 | mossgolem | Hollow King | Phase 2 tell hard to read | high | 100 | Carlos | addressed
2026-01-20 | saltlantern | Inventory | Drag drop drops item off grid | high | 90 | Tyler | in progress
2026-01-20 | quietfox88 | Tutorial | Dash hint appears too late | low | 60 | Carlos | addressed
2026-01-27 | hollowtide | Audio | Rain zone music clips when looping | medium | 70 | Tyler | in progress
2026-02-03 | pixelwren | Act 2 marsh | Hidden path not signposted | low | 40 | Carlos | wont fix
2026-02-10 | mossgolem | Boss arena | Door soft locks after death | high | 30 | Tyler | fixed
2026-02-17 | saltlantern | Performance | Frame dips on low end GPU | medium | 55 | Tyler | investigating
2026-02-17 | quietfox88 | Onboarding | Level-select back-out unclear | medium | 65 | Carlos | in progress
2026-02-19 | hollowtide | Narrative | Drowned Bell scene skippable by accident | low | 25 | Carlos | backlog
2026-02-19 | pixelwren | Combat | Parry window feels 1 frame short | medium | 50 | Carlos | investigating
2026-02-21 | mossgolem | Inventory | Stack count not refreshing after use | low | 45 | Tyler | backlog
Open high-severity | 1
Open medium-severity | 4
Fixed / addressed | 4
Won't fix | 1
Launch-risk items (open, sev>=medium) | 5