## Slide 1
Operations and Opening Plan
Rootstock | Build, staff, and open
Prepared by Cynthia Thornton, Chef-Owner | October 2026 | Confidential

## Slide 2
Timeline to Opening
Q4 2026
Lease and LOI, investor close
Q1 2027
Financing and permits
Q2 2027
Buildout and hiring
Q3 2027
Open the doors
Sequenced deliberately. Each phase only starts when the prior one is funded and signed. No opening before the kitchen is dialed.

## Slide 3
Use of Funds
Total project 465,000 dollars
Buildout
185k
Equipment
95k
Furniture
48k
Permits
30k
Payroll
35k
Smallwares
22k
Inventory
18k
Reserve
32k
Funded by 50,000 owner equity, a 165,000 SBA 7(a) loan, and 250,000 investor equity.

## Slide 4
Opening Brigade
Chef-Owner
Cynthia Thornton. Menu, sourcing, the line.
Sous chef
One hire. Runs service when I am in the office.
Line cooks
Three. Saute, grill, garde manger.
Pastry
One. Bread service and desserts.
General manager
Experienced FOH lead, hired before opening.
Advisor
Frank Benedetto, 25 years running a room.

## Slide 5
Risk and Mitigation
High first-year failure rate
Conservative cover count and a 32,000 working capital cushion.
Food cost volatility
Direct farm buying and a 30 percent food cost target, reviewed weekly.
Labor pressure
Owner on the line at opening, tight brigade, cross-trained stations.
Slow ramp
Lower break-even at 233 covers per week, modest year-one revenue.

## Slide 6
Next Steps
1
Finish the financial model before the November 2, 2026 review.
2
Sign a lease or letter of intent on the lead Hoboken space.
3
Close investor equity and get SBA pre-qualified.
4
Keep owner equity climbing toward the 50,000 target.