# Q4 2026 Corporate Inspection Prep Plan

Grand Sierra Hotel, Housekeeping Floors 12 to 18. Prepared by Chris Murray, Floor Supervisor. Plan dated February 9, 2026.

Inspection target date: Tuesday, November 10, 2026. Corporate quality team walks all guest floors. Goal is a clean pass with zero repeat findings from the 2025 review.

## Carryover Findings From 2025 To Close First

Shower track buildup on floors 14 and 16. Add the deep track scrub to the weekly rotation.

Inconsistent minibar par counts. Reprint par sheets and laminate one per VIP room class.

Linen closet labeling on 12 and 18. Relabel shelves and assign a daily tidy owner.

## Workstream 1: People

Finish onboarding the three new hires by February 20, 2026, then run two refresher huddles before the fall.

Pair each new hire with a senior housekeeper for VIP rooms until sign off.

Confirm Yolanda Reynolds leads the floor 16 readiness check, she catches what others miss.

## Workstream 2: Rooms and Standards

Run a mock inspection on October 20, 2026 using the corporate scorecard.

Fix every mock finding within five business days and log it on the tracker.

Spot check ten random rooms per floor each week through October 2026.

## Workstream 3: Supplies and Equipment

Audit cart inventory and replace worn caddies and cracked spray bottles.

Confirm vacuum belts and filters are serviced before November.

Hold a two week amenity buffer so no room is short on inspection day.

## Reporting

Weekly readiness note to Gerald Patterson, General Manager, starting October 1, 2026. Escalate any finding that needs budget or staffing the same day it appears. The plan is simple: close the old findings early, keep the new people sharp, and walk the floors like the inspector already arrived.