## Slide 1
Q4 Corporate Inspection
Readiness Plan, Floors 12 to 18. Inspection target: November 10, 2026.
Grand Sierra Hotel | Housekeeping Readiness

## Slide 2
Close These First
• Shower track buildup on floors 14 and 16, add deep scrub to weekly rotation
• Inconsistent minibar par counts, reprint and laminate one sheet per VIP class
• Linen closet labeling on 12 and 18, relabel shelves and assign a daily owner
Grand Sierra Hotel | Housekeeping Readiness

## Slide 3
Three Workstreams
People
• Finish onboarding 3 new hires
• Pair each with a senior for VIP
• Yolanda leads floor 16 check
Rooms and Standards
• Mock inspection October 20
• Fix findings within 5 days
• Spot check 10 rooms per floor
Supplies
• Replace worn caddies
• Service vacuum belts and filters
• Hold a two week amenity buffer
Grand Sierra Hotel | Housekeeping Readiness

## Slide 4
Reporting and Goal
• Weekly readiness note to Gerald Patterson starting October 1, 2026
• Escalate any finding that needs budget or staffing the same day
• Goal is a clean pass with zero repeat findings from the 2025 review
Close the old findings early, keep the new people sharp, walk the floors like the inspector already arrived.
Grand Sierra Hotel | Housekeeping Readiness