## Punchlist
unit | panel_size_amps | change_order_ref | as_built_status | walkthrough_notes | warranty_start_target
1 | 200 | CO-HV-001 | complete | Confirmed by Ryan 09/12; tenant signed off | 2026-10-08
2 | 200 | CO-HV-002 | complete | Confirmed by Ryan 09/12 | 2026-10-08
3 | 200 | CO-HV-003 | complete | Confirmed by Danny 09/13 | 2026-10-08
4 | 200 | CO-HV-004 | complete | Confirmed by Danny 09/13 | 2026-10-08
5 | 200 | CO-HV-005 | complete | Confirmed by Ryan 09/14 | 2026-10-08
6 | 200 | CO-HV-006 | complete | Confirmed by Ryan 09/14; minor label correction pending | 2026-10-08
7 | 200 | CO-HV-007 | complete | Ryan lead; verified 09/16 | 2026-10-08
8 | 200 | CO-HV-008 | complete | Ryan lead; verified 09/16 | 2026-10-08
9 | 200 | CO-HV-008-A | complete | Change order CO-HV-008-A added 09/04 for additional kitchen circuit | 2026-10-08
10 | 200 | CO-HV-010 | complete | Ryan lead; verified 09/17 | 2026-10-08
11 | 200 | CO-HV-011 | complete | Ryan lead; verified 09/17 | 2026-10-08
12 | 200 | CO-HV-012 | complete | Ryan lead; verified 09/17 | 2026-10-08
13 | 200 | CO-HV-013 | complete | Danny/Jake; verified 09/19 | 2026-10-08
14 | 200 | CO-HV-014 | open | Island GFCI on separate breaker per code; owner question via Maria Suarez 09/18 needs canned answer | 2026-10-08
15 | 200 | CO-HV-015 | complete | Danny/Jake; verified 09/19 | 2026-10-08
16 | 200 | CO-HV-016 | complete | Danny/Jake; verified 09/20 | 2026-10-08
17 | 200 | CO-HV-017 | complete | Danny/Jake; verified 09/20 | 2026-10-08
18 | 200 | CO-HV-018 | complete | Danny/Jake; verified 09/20 | 2026-10-08
19 | 200 | CO-HV-019 | complete | Ryan; verified 09/22 | 2026-10-08
20 | 200 | CO-HV-020 | complete | Ryan; verified 09/22 | 2026-10-08
21 | 200 | CO-HV-021 | complete | Ryan; verified 09/23 | 2026-10-08
22 | 200 | CO-HV-022 | complete | Ryan; verified 09/23 | 2026-10-08
23 | 200 | CO-HV-023 | pending-re-verify | Stale punch entry says incomplete; field photo 09/24 shows complete - confirm in person before inspection | 2026-10-08
24 | 200 | CO-HV-024 | complete | Ryan; verified 09/25 | 2026-10-08