## Schedule
date | shift | site | ryan_omalley | danny_flores | jake_parsons | expected_hours | notes
2026-10-01 | 07:00-16:00 | Harborview Walker's Point | lead | assigned | assigned | 9 | Final punch closeout
2026-10-02 | 07:00-16:00 | Harborview Walker's Point | lead | assigned | assigned | 9 | Final punch closeout
2026-10-05 | 07:00-13:00 | Harborview Walker's Point | lead | assigned | off | 6 | Originally inspection day - rescheduled
2026-10-06 | 07:00-16:00 | Harborview Walker's Point | lead | assigned | assigned | 9
2026-10-07 | 07:00-16:00 | Service calls | off | lead | assigned | 9 | Ryan PTO half-day
2026-10-08 | 08:00-14:00 | Harborview Walker's Point | lead | assigned | assigned | 6 | FINAL INSPECTION with Dan Mitchell - rescheduled from 10/05
2026-10-09 | 07:00-16:00 | Service calls + warranty calls | lead | assigned | assigned | 9 | Heaton callback queued
2026-10-12 | 07:00-16:00 | Bay View pre-mob materials staging | lead | off | assigned | 9 | Danny PTO
2026-10-13 | 07:00-16:00 | Service calls | assigned | lead | assigned | 9
2026-10-14 | 07:00-16:00 | Bay View pre-mob | lead | assigned | assigned | 9
2026-10-15 | 07:00-15:00 | Service calls | lead | assigned | assigned | 8 | Jae at IBEW meeting 18:00
2026-10-16 | 07:00-16:00 | Service calls | lead | assigned | assigned | 9 | Jake half-day for personal
2026-10-19 | 07:00-16:00 | Bay View pre-mob materials confirm | lead | assigned | assigned | 9 | Bronze EMT order deadline - by EOD per supplier
2026-10-20 | 07:00-16:00 | Service calls | lead | assigned | assigned | 9
2026-10-21 | 07:00-16:00 | Bay View pre-mob | lead | assigned | assigned | 9 | Solar quote sheet expires today
2026-10-22 | 07:00-16:00 | Service calls | lead | assigned | assigned | 9
2026-10-23 | 07:00-16:00 | Bay View pre-mob | lead | assigned | assigned | 9
2026-10-26 | 07:00-16:00 | Service calls + solar discovery visits | lead | assigned | assigned | 9 | Janet Kowalski + Jia Nguyen site walks if confirmed
2026-10-27 | 07:00-16:00 | Bay View pre-mob | lead | assigned | assigned | 9
2026-10-28 | 07:00-16:00 | Service calls | lead | assigned | assigned | 9 | Jae chiropractor 17:00
2026-10-29 | 07:00-16:00 | Bay View pre-mob | lead | assigned | assigned | 9 | Final tool inventory and truck loadout
2026-10-30 | 07:00-16:00 | Service calls | lead | assigned | assigned | 9
2026-11-02 | 07:00-16:00 | Bay View Historic Home KICKOFF 2247 S Kinnickinnic | lead | assigned | assigned | 9 | Owner away Nov 2-20; key with Mr Krebs at 2245