DRAFT - NOT SENT

From: angela.peterson@Greenridertech.co.in

To: k.palani@yahoo.com

Date: December 19, 2025

Subject: Q1 2026 Field Schedule - Proposed Plan + Station C Monitoring

Dr. Palani,

With the holidays coming up I want to get the Q1 dive schedule locked in before everyone checks out. After the November Station C flag (5.1% bleaching) I think we should increase monitoring frequency there in January and February rather than sticking to the standard monthly cadence.

January 2026

Jan 8-9: Waikiki Reef A, B, C (two divers; Rodriguez on B transects)

First C transect since November flag - need the January baseline reading

Jan 22-23: Hanauma Bay A, B (Rodriguez solo if I am on data QC that week)

Jan 29-30: Waikiki Reef B makeup + Lanai Lookout A revisit (confirm Dec baseline)

February 2026

Feb 5-6: Hanauma Bay A, B

Feb 19-20: Waikiki Reef C - priority dive; if bleaching hits 6%+ we file formal alert

Rodriguez confirmed availability through January. I will check with Malia about boat scheduling for Feb 19-20 - that week fills up fast.

The December 11 Lanai Lookout baseline looked solid: 37.2% cover, 2.4% bleaching, 24m visibility. One revisit should confirm stability before we bring it into regular rotation.

Let me know if you want to adjust before I send the January request to the dive team.

Angela