## Slide 1
PSSA BOARD PLANNING
Harbor Point University Saturday 2027-10-24, 7:00 PM Student Center
Fall Mixer Planning Deck
Kick off the term and drive membership

## Slide 2
Goal
Allen Weber | PSSA Co-Chair, 2027 to 2028
2
Kick off the term and drive membership.
Target attendance of 120 or more.
Make signing up effortless at the door.
Preview the election watch party and the grad school panel.

## Slide 3
Budget
Allen Weber | PSSA Co-Chair, 2027 to 2028
3
Line | Planned USD
Catering deposit | 220
Supplies and name tags | 45
Total | 265
Funded by dues
The fall budget is conservative, funded by dues and ticket sales. The election watch party stays under the 50 dollar supply threshold. Tracked in workbook X05.

## Slide 4
Timeline
Allen Weber | PSSA Co-Chair, 2027 to 2028
4
Time | Segment
7:00 PM | Doors and check-in
7:20 PM | Welcome remarks
7:30 PM | Icebreaker mixer
8:10 PM | Open networking
8:45 PM | Membership pitch
9:30 PM | Teardown

## Slide 5
Roles
Allen Weber | PSSA Co-Chair, 2027 to 2028
5
Lead and check-in: Allen Weber.
Catering and supplies: board partner.
Greeter and name tags: board member.
Music and slides: board member.

## Slide 6
Risks and asks
Allen Weber | PSSA Co-Chair, 2027 to 2028
6
Low turnout: push a reminder one week out through the member group chat.
AV failure: keep a phone speaker as backup.
Board ask: confirm the catering order two days ahead.
Board ask: bring two volunteers for teardown.