## Chapters
Chapter | Title | Art | Code | Writing | Audio (Ravi) | Percent | Notes
1 | The Lantern Festival | Done | Done | Done | Done | 100 | vertical slice opener
2 | The General Store | Done | Done | Done | Done | 100 | shop barter puzzle working
3 | The River Road | Done | Done | Done | In progress | 90 | bridge softlock fixed in 0.6.3
4 | The Night Sky | In progress | In progress | Draft | Not started | 45 | star refs from NASA, demo target scene
5 | The Bakery | Outline | Not started | Outline | Not started | 10 | warm light pass planned
6 | The Letter | Outline | Not started | Draft | Not started | 10 | the grandma voice chapter
7 | The Long Way Home | Outline | Not started | Outline | Not started | 5 | finale
Vertical slice | roughly 60 percent complete
Showcase demo | Cascadia Indie Showcase 2026-11-08
Demo scope | Chapters 1 to 3 polished plus Chapter 4 teaser
Current build | 0.6.5-vslice
Telemetry | itch.io devlog, Sentry crash capture, PostHog playtest events