## Slide 1
SEASONAL READINESS PLAN
Prom and Spring Peak
Getting all three locations ready for the 2027 spring rush
Planning review: November 2026
Peak window
April to May
Q2 is the strongest quarter of the year

## Slide 2
Why the Spring Peak Matters
$334,500
Q2 revenue, prior year
Main St
Books out first, every year
3 tiers
Prom packages, $75 to $99
Prom weekends fill fast, especially at the Main Street flagship
Clients bring a dress color or photo and expect a match, so polish stock matters
Lash extensions at Wheaton add an upsell if the esthetics launch lands in time

## Slide 3
The Prom Package Menu
The Classic
$75
Gel manicure and express pedicure
The Showstopper
$95
Full set acrylic with custom art
The Glam
$99
Dip powder, art, and paraffin treatment
Groups of four or more save 10 percent per person

## Slide 4
Staffing for the Rush
Chart: 
| Main Street | Orchard Plaza | Wheaton
Active techs | 11 | 9 | 8
Target for peak | 13 | 10 | 9
The gap
Two Orchard Plaza techs left recently. Interviews underway to fill before April.
Hold weekend hours steady. Do not cut staff to absorb the rent increase.

## Slide 5
Readiness Checklist
Order extra polish, gel, and chrome stock by February, ahead of the March booking open
Confirm prom-package pricing and group discount across all three desks
Fill the two open Orchard Plaza chairs and set the weekend schedule
Push early booking, especially Main Street, through the design board and front desk
Decide whether Wheaton lash is ready to feature as a prom upsell