Wheaton Expansion: Waxing and Lash Services

Location: 314 Danada Square West, Wheaton, IL 60189. Manager: Ryan Novak.

Prepared by Cecilia Burnett, February 2026.

The idea

Wheaton has the room and the younger client base to carry esthetic services. Adding brow and lip waxing and full lash extensions opens a second revenue line that does not depend on a nail chair turning over. The Main Street and Orchard Plaza menus stay nails only for now.

Licensing

Illinois licenses esthetics separately from cosmetology. Waxing and lash work require a licensed esthetician on site. Two options:

Hire a licensed esthetician. Faster, but adds payroll before the service proves itself.

Sponsor Ryan or a current tech through the 750 hour esthetics program at an approved school, then license. Slower, but keeps it in house.

What it costs to start

Waxing station build out and supplies: about 1,400. Lash chair, lamp, and starter kits: about 2,100. Both sit under separate purchase approvals. Anything at or above 500 comes to me first.

What it could earn

Full lash sets price at 120. A single esthetician booking four sets a day, five days a week, runs close to 9,600 a month in lash revenue before fills and waxing. Conservative target for year one is to clear the added payroll and supplies by month five.

Open questions

Confirm the exact current esthetics hour requirement with the state board.

Decide hire versus sponsor by April.

Check the Wheaton lease for any use restrictions on esthetic services.