## Milestones
rustpath, milestone tracker
Personal Rust learning project, Saturday afternoons.
Fast filesystem path inspection and manipulation CLI, written from scratch.
Licensed to a small number of companies; the receipts sit with the processor, not here.
Task | Status | Target | Effort | Notes
Project setup, cargo and CI | Done | 01/10/2026 | Low | Repo plus basic workflow
Argument parsing with clap | Done | 01/24/2026 | Low | inspect, walk, match, stats
Path record struct and TSV read/write | Done | 02/07/2026 | Medium | serde, hand-rolled parse first
Glob and pattern matching engine | Done | 02/21/2026 | High | The part that taught me lifetimes
Parallel directory walk | Done | 03/07/2026 | High | rayon, then benchmarked against a naive walk
Error handling pass, no unwrap in library code | Done | 03/21/2026 | Medium | thiserror, proper Result plumbing
Cross-platform path normalisation | Done | 04/04/2026 | High | Windows separators are their own project
Benchmark suite | Done | 04/18/2026 | Medium | criterion, tracks regressions
Man page and help text | Done | 05/02/2026 | Low | Written before the feature freeze, deliberately
1.0 release and licence terms | Done | 05/16/2026 | Medium | Indie, Team, Enterprise tiers
Licence key validation, offline | Done | 06/06/2026 | High | No phone home; keys verify locally
Support and maintenance retainer offer | Done | 06/20/2026 | Low | For the enterprise seats
Windows installer | In progress | 10/24/2026 | Medium | The last real gap
Shell completions, bash and zsh | In progress | 11/07/2026 | Low | Half written
Plugin interface | To do | 12/05/2026 | High | Only if the design holds up
Docs site refresh | To do | 12/19/2026 | Medium | Ties to the reading-notes site work
2.0 scope decision | To do | 01/16/2027 | Medium | Depends on what the leave looks like
Licence tier | Price | Seats | Notes
rustpath Indie License | 49 | Single developer | Card, self-serve
rustpath Team License | 299 | Up to 10 developers | Card or invoice
rustpath Enterprise License | 1200 | Site licence | Invoice, annual
Support and maintenance retainer | 450 | Add-on | Enterprise only
Open-source sponsorship | 100 | n/a | Goodwill, not a licence
The ledger side of this lives with the CPA, not on this sheet.
I have never reconciled the tiers here against what actually cleared.